ATLAS™ TOOLKIT

ATLAS™ CONTRACT ADMINISTRATION IMPLEMENTATION GUIDE

Deployment of the Six Essential Toolkits

A management guide for rolling out the toolkit across a project, business unit or contracting organisation.

# Recommended Deployment Model

| Week / Stage | Action | Output | Owner |
| --- | --- | --- | --- |
| Mobilisation | Map contract and set administration calendar | Toolkit 1 completed | Lead CA |
| Week 1 | Launch notice, change, delay, payment and evidence registers | Toolkits 2–6 live | CA / Commercial / Planner |
| Weekly | Contract administration review meeting | Deadlines, notices, change, delay and claims reviewed | Project Manager |
| Monthly | Management contract health review | Exposure dashboard and decisions | Project Director / CXO |
| Major Event | Activate event workflow | Clause, notice, evidence, time and money position | Event Owner |
| Close-Out | Reconcile unresolved matters and archive evidence | Final account / claim / record close-out | Lead CA |

# Standing Weekly Contract Administration Agenda

1.  Time bars and notices due in the next 14 days

2.  New instructions and potential variations

3.  Pending variation quotations and approvals

4.  Current delay events, programme effect and mitigation

5.  EOT notices and submissions

6.  Payment applications, certificates and overdue payment

7.  Claims and responses due

8.  Evidence gaps and document control issues

9.  Risk / dispute escalation decisions

10.  Actions, owners and deadlines

# Recommended Issue Reference Convention

Use one common reference to connect records across all six toolkits. Example: EVT-2026-014. The same reference should appear on the notice, change register, delay register, claim assessment and evidence matrix where the event is related.

# Minimum Governance

Lead Contract Administrator owns the overall system.

Project Manager chairs the weekly review and enforces action ownership.

Planner owns programme evidence and delay analysis.

Commercial / QS owns valuation, payment and quantum.

Document Controller owns controlled filing and proof of transmission.

Senior management reviews unresolved high-value / high-time exposure monthly.

SUCCESS TEST At any point, management should be able to ask: What happened? Which clause applies? Was notice issued? What is the time effect? What is the money effect? What evidence do we have? Who owns the next action? The toolkit is working when those answers can be produced quickly.