ATLAS™

CONTRACT ADMINISTRATOR
PROFESSIONAL TOOLKIT

The 6 Essential Toolkits for Better Construction Contract Administration

THE SIX DISCIPLINES 1 KNOW THE CONTRACT • 2 PROTECT YOUR RIGHTS • 3 CONTROL THE CHANGE • 4 PROTECT THE TIME • 5 PROTECT THE MONEY • 6 PROTECT THE EVIDENCE

Implementation Edition

# How to Use This Pack

This pack is designed to be implemented on live construction projects. Each toolkit combines a visual workflow, decision/checklist tools, editable forms and registers, and an implementation routine. The tools are contract-form neutral: users must insert the actual clause references, notice periods, terminology and procedures from the signed contract and applicable law.

1.  Mobilise the six core registers at project commencement.

2.  Assign a named owner for each register and template family.

3.  Review deadlines, change, delay and claims in a standing weekly contract administration meeting.

4.  Cross-reference issues between the notice, variation, delay, payment and evidence tools using a common issue reference.

5.  Archive closed matters and record lessons learned at project close-out.

ATLAS™ TOOLKIT 1

KNOW THE CONTRACT

Contract Interpretation & Clause Navigation

Build a one-page operating map of the contract so that the project team can identify obligations, procedures, deadlines and consequences quickly.

# Use & Adaptation Note

This toolkit is a practical contract administration aid. It is intentionally contract-form neutral. Before use, adapt clause references, notice periods, service requirements, terminology, statutory requirements and dispute procedures to the signed contract, its amendments and the governing law. It does not replace project-specific legal advice where legal advice is required.

# 1. Contract Particulars Sheet

| Project |  |
| --- | --- |
| Employer |  |
| Contractor |  |
| Contract Administrator / Engineer |  |
| Contract Form & Edition |  |
| Contract Date |  |
| Contract Sum |  |
| Commencement Date |  |
| Time for Completion / Completion Date |  |
| Defects / DLP Period |  |
| Governing Law |  |
| Dispute Mechanism |  |
| Seat / Venue |  |
| Liquidated Damages / Delay Damages |  |
| Retention |  |
| Performance Security |  |
| Advance Payment |  |
| Key Insurance Requirements |  |

## 2. Contract Document Hierarchy / Order of Precedence

| Contract Document | Date / Revision | Order of Precedence | Stored Location | Reviewed By |
| --- | --- | --- | --- | --- |

## 3. Key Clause Map

| Subject | Clause | Key Procedure | Deadline / Period | Responsible Person |
| --- | --- | --- | --- | --- |

## 4. Contractual Obligation Matrix

| Party | Obligation | Trigger | Deadline | Required Action / Output | Consequence of Failure |
| --- | --- | --- | --- | --- | --- |

## 5. Time-Bar & Deadline Alert Register

| Event / Obligation | Clause | Trigger Date | Notice Due | Claim / Detail Due | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |

## 6. Contract Review Checklist

☐ Signed agreement and amendments located

☐ Particular / Special Conditions reviewed against General Conditions

☐ Definitions relevant to administration highlighted

☐ Document precedence confirmed

☐ Notice method and addresses confirmed

☐ Time bars and condition precedents extracted

☐ Payment procedure and certification dates mapped

☐ Variation procedure mapped

☐ Delay / EOT procedure mapped

☐ Suspension and termination procedures mapped

☐ Security, insurance and retention requirements recorded

☐ Dispute escalation mechanism mapped

GOLDEN RULE Never read a clause in isolation. Check the definition, related clauses, Particular Conditions / amendments, governing law and the consequence of non-compliance.

# Implementation on a Live Project

1.  Complete the Contract Particulars Sheet before the first administration meeting.

2.  Build the Clause Map from the signed contract, not from a standard unamended form.

3.  Load every time bar and recurring deadline into the Deadline Register.

4.  Review the Obligation Matrix with commercial, planning and project leadership.

5.  Keep the Clause Map available in weekly project meetings and update it when amendments or supplemental agreements are issued.

## Minimum Ownership

| Role | Responsibility |
| --- | --- |
| Contract Manager / Lead CA | Own the contract map and legal/contractual interpretation workflow. |
| Project Manager | Ensure operational teams understand major obligations and triggers. |
| Planner | Integrate contractual time requirements and programme obligations. |
| Commercial / QS | Map payment, valuation, claims and final account provisions. |

IMPLEMENTATION PRINCIPLE A toolkit only adds value when someone owns it, deadlines are reviewed routinely, and project teams actually use the outputs in meetings and decisions.

ATLAS™ TOOLKIT 2

PROTECT YOUR RIGHTS

Notices, Correspondence & Communication

Preserve contractual rights by making notices timely, valid, factual, traceable and connected to the relevant clause and event.

# Use & Adaptation Note

This toolkit is a practical contract administration aid. It is intentionally contract-form neutral. Before use, adapt clause references, notice periods, service requirements, terminology, statutory requirements and dispute procedures to the signed contract, its amendments and the governing law. It does not replace project-specific legal advice where legal advice is required.

## 1. The 6-Point Notice Validity Test

☐ WHO must issue the notice?

☐ TO WHOM must it be sent?

☐ WHAT event / contractual matter is being notified?

☐ WHEN must it be issued?

☐ HOW must it be served?

☐ WHERE / to which contractual address or platform must it be sent?

## 2. Master Notice Register

| Ref | Event | Clause | Event Date | Notice Due | Notice Issued | Method / Recipient | Follow-up Due | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## 3. Master Contractual Notice Template

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: NOTICE OF [EVENT / MATTER]

We refer to [instruction / event / circumstance] occurring on [date].

The [Contractor / Employer / Party] hereby gives notice pursuant to Clause [X] that [concise factual description of the event].

The event has caused and/or is likely to cause an effect upon [time / cost / sequence / productivity / access / resources]. The full consequences are continuing to be assessed.

The [Contractor / Employer / Party] reserves all contractual and legal rights arising from this matter, including any entitlement to additional time and/or payment where applicable.

Further particulars and supporting records will be provided in accordance with the Contract. Please acknowledge receipt.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

## 4. Notice of Delay

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: NOTICE OF DELAY / DELAY EVENT

We refer to [event / instruction / certificate] dated [date].

The event is affecting or is likely to affect Activity [ID / description] and may affect the Time for Completion. Contemporaneous records and programme impact are being maintained.

This correspondence is issued without prejudice to any other entitlement or remedy available under the Contract and applicable law.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

## 5. Notice of Variation / Change

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: NOTICE OF VARIATION / CHANGE

We refer to [event / instruction / certificate] dated [date].

We consider the instruction / revised information to constitute or potentially constitute a change to the contractual scope. The resulting time and cost consequences are being assessed.

This correspondence is issued without prejudice to any other entitlement or remedy available under the Contract and applicable law.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

## 6. Notice of Claim

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: NOTICE OF CLAIM

We refer to [event / instruction / certificate] dated [date].

This notice is issued to preserve entitlement arising from [event]. The contractual and factual basis, impact and quantum will be particularised in accordance with the Contract.

This correspondence is issued without prejudice to any other entitlement or remedy available under the Contract and applicable law.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

## 7. Notice of Late Information / RFI Impact

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: NOTICE OF LATE / OUTSTANDING INFORMATION

We refer to [event / instruction / certificate] dated [date].

The information identified above is required by [required date] to avoid impact to [activity / procurement / workfront]. Please provide the required information / instruction.

This correspondence is issued without prejudice to any other entitlement or remedy available under the Contract and applicable law.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

## 8. Reservation of Rights

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: RESERVATION OF RIGHTS

We refer to [event / instruction / certificate] dated [date].

Nothing in ongoing performance, discussions, mitigation measures or interim arrangements is intended to waive any contractual or legal right. All rights are expressly reserved.

This correspondence is issued without prejudice to any other entitlement or remedy available under the Contract and applicable law.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

## 9. Notice of Non-Payment

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: NOTICE OF NON-PAYMENT / OVERDUE PAYMENT

We refer to [event / instruction / certificate] dated [date].

Payment due under [certificate / application / clause] remains outstanding. Please arrange payment and confirm the remittance position in accordance with the Contract.

This correspondence is issued without prejudice to any other entitlement or remedy available under the Contract and applicable law.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

## 10. Correspondence Quality Control

☐ Use facts, dates and document references

☐ State the required action clearly

☐ Identify the clause where appropriate

☐ Avoid unnecessary admissions or emotive language

☐ Attach supporting documents or identify where they are stored

☐ State a response date where needed

☐ Preserve rights where the full impact is not yet known

☐ Confirm service in the contractually permitted manner

☐ Enter the issue in the Notice Register

GOLDEN WORKFLOW EVENT → CLAUSE → NOTICE → RECORD → IMPACT → ENTITLEMENT → CLAIM / RESPONSE → CLOSE-OUT

# Implementation on a Live Project

1.  Create the Master Notice Register on Day 1.

2.  Pre-address the approved notice templates with contractual addresses and service methods.

3.  Review notice deadlines at least weekly and during every major event meeting.

4.  Require verbal instructions with contractual significance to be confirmed in writing.

5.  Link every notice to an evidence folder and to the associated change, delay or claim register.

## Minimum Ownership

| Role | Responsibility |
| --- | --- |
| Contract Administrator | Draft, validate, issue and log notices. |
| Project Manager | Escalate operational events promptly. |
| Planner / Commercial | Provide time and cost implications for follow-up particulars. |
| Document Controller | Maintain proof of issue, receipt and filing. |

IMPLEMENTATION PRINCIPLE A toolkit only adds value when someone owns it, deadlines are reviewed routinely, and project teams actually use the outputs in meetings and decisions.

ATLAS™ TOOLKIT 3

CONTROL THE CHANGE

Variation & Change Management

Make project change visible, authorised, measured, valued and closed so that additional scope does not become unrecoverable work.

# Use & Adaptation Note

This toolkit is a practical contract administration aid. It is intentionally contract-form neutral. Before use, adapt clause references, notice periods, service requirements, terminology, statutory requirements and dispute procedures to the signed contract, its amendments and the governing law. It does not replace project-specific legal advice where legal advice is required.

## 1. Variation Identification Test

☐ Has scope changed?

☐ Has quantity changed?

☐ Has quality / specification changed?

☐ Has sequence changed?

☐ Has method or access changed?

☐ Have working hours or constraints changed?

☐ Has additional testing or coordination been required?

☐ Has a drawing / instruction created extra work?

☐ Has an omission affected remaining work?

☐ Has acceleration or resequencing been requested?

## 2. Change Control Initiation Form

| Change Ref |  |
| --- | --- |
| Date Identified |  |
| Source / Instruction Ref |  |
| Originator |  |
| Description of Original Requirement |  |
| Description of Changed Requirement |  |
| Contract Clause / Basis |  |
| Notice Required? |  |
| Time Impact Potential |  |
| Cost Impact Potential |  |
| Authorisation Status |  |
| Responsible Owner |  |

## 3. Variation / Change Register

| VO / Change No. | Description | Instruction Date | Notice Date | Quotation | Submitted Value | Approved Value | Time Impact | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## 4. Variation Pricing Sheet

| Cost Component | Basis / Quantity | Rate | Amount | Supporting Record |
| --- | --- | --- | --- | --- |

Labour

Materials

Plant / equipment

Subcontractors

Preliminaries / time-related cost

Attendance

Overheads

Profit

Design / testing

Other contractual adjustments

## 5. Daywork / Force Account Record

| Date | Work Area | Labour / Trade | Hours | Plant / Equipment | Materials | Supervisor Sign-off |
| --- | --- | --- | --- | --- | --- | --- |

## 6. Constructive Change Warning Signs

☐ Revised drawing without formal variation wording

☐ Additional specification or test requirement

☐ Repeated rejection of otherwise compliant work

☐ Restricted access or altered workfront

☐ Changed sequence / phasing

☐ Additional coordination or temporary works requirement

☐ Request to recover programme without formal EOT decision

☐ Late information requiring changed method

☐ Instruction given in meeting minutes or email rather than formal instruction

## 7. Variation Close-Out Register

| Change No. | Agreed Scope? | Agreed Value? | Time Agreed? | Certificate / Payment Ref | Final Account Included? | Closed Date |
| --- | --- | --- | --- | --- | --- | --- |

GOLDEN RULE Do not wait for the final account to discover that the project changed. Identify, notify, record and value change while the facts are current.

# Implementation on a Live Project

1.  Require every instruction or revised document with potential scope effect to be screened through the Variation Identification Test.

2.  Assign a unique change reference immediately.

3.  Issue contractual notice before the applicable deadline.

4.  Start cost and time records from the first day of impact.

5.  Review pending changes weekly and reconcile approved values into payment and final account records.

## Minimum Ownership

| Role | Responsibility |
| --- | --- |
| Site / Engineering | Identify field changes and provide technical description. |
| Contract Administrator | Determine contractual pathway and notice. |
| QS / Commercial | Measure, value and reconcile. |
| Planner | Assess schedule effect. |
| Project Manager | Manage authority and escalation. |

IMPLEMENTATION PRINCIPLE A toolkit only adds value when someone owns it, deadlines are reviewed routinely, and project teams actually use the outputs in meetings and decisions.

ATLAS™ TOOLKIT 4

PROTECT THE TIME

Delay, EOT & Programme Management

Connect delay events to contractual risk and programme effect, then preserve and demonstrate entitlement to time where applicable.

# Use & Adaptation Note

This toolkit is a practical contract administration aid. It is intentionally contract-form neutral. Before use, adapt clause references, notice periods, service requirements, terminology, statutory requirements and dispute procedures to the signed contract, its amendments and the governing law. It does not replace project-specific legal advice where legal advice is required.

## 1. Delay Event Register

| Delay Ref | Event | Start | End | Responsible Risk | Affected Activity | Critical? | Notice Ref | EOT Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

# 2. Delay Assessment Worksheet

| Delay Ref |  |
| --- | --- |
| What happened? |  |
| When did it begin? |  |
| When did it end / is it ongoing? |  |
| Why did it happen? |  |
| Who bears the contractual risk? |  |
| Affected programme activity / WBS |  |
| Critical path impact? |  |
| Float available? |  |
| Notice clause and deadline |  |
| Notice reference |  |
| Mitigation actions |  |
| Concurrent delay issues |  |
| Estimated EOT impact |  |
| Supporting evidence location |  |

## 3. EOT / Delay Notice Template

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: NOTICE OF DELAY AND POTENTIAL EXTENSION OF TIME

We refer to [event / instruction / circumstance] which commenced on [date].

The event is affecting or is likely to affect [activity / workfront] and may delay the Time for Completion. This notice is issued pursuant to Clause [X].

The event remains [ongoing / concluded]. Programme impact, mitigation and any concurrent effects are being assessed. Updated particulars will be provided in accordance with the Contract.

All rights to an extension of time and associated monetary entitlement, where the Contract provides for such entitlement, are reserved.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

# 4. EOT Claim Submission Structure

1.  Executive summary and relief sought

2.  Contractual entitlement and relevant clauses

3.  Factual chronology

4.  Cause of delay

5.  Programme methodology and contemporaneous programme records

6.  Cause-and-effect analysis

7.  Critical path / completion impact

8.  Mitigation undertaken

9.  Concurrency analysis where applicable

10.  EOT calculation

11.  Supporting evidence index

12.  Conclusion and requested determination

## 5. Delay Evidence Checklist

☐ Accepted baseline programme

☐ Updated / revised programmes

☐ Progress reports

☐ Site diaries

☐ Progress photographs

☐ Instructions

☐ RFI and drawing registers

☐ Meeting minutes

☐ Labour and plant records

☐ Procurement records

☐ Subcontractor records

☐ Access records

☐ Weather records where relevant

☐ Delay notices and acknowledgements

☐ Mitigation correspondence

☐ Acceleration instructions / requests

## 6. Delay Responsibility Matrix

| Delay Event | Employer Risk | Contractor Risk | Neutral / Shared | Clause | Notes |
| --- | --- | --- | --- | --- | --- |

## 7. Mitigation Log

| Date | Delay Ref | Mitigation Action | Resources / Cost | Expected Benefit | Actual Result | Evidence Ref |
| --- | --- | --- | --- | --- | --- | --- |

## 8. Acceleration Alert Checklist

☐ Has the contractual completion date changed?

☐ Has an EOT been granted or refused?

☐ Is acceleration expressly instructed or merely requested?

☐ Is there an agreed acceleration scope and target date?

☐ Who bears additional cost?

☐ Are additional resources / shifts / resequencing required?

☐ Are productivity and cost records being kept?

☐ Is the instruction properly authorised?

GOLDEN RULE Delay is not merely an event. It must be connected to contractual risk, programme effect, causation, mitigation and the relief sought.

# Implementation on a Live Project

1.  Open a Delay Ref as soon as a material event is identified.

2.  Issue the contractual notice before the deadline; do not wait for full impact to be known unless the contract says otherwise.

3.  Ask the planner to identify the affected activity and contemporaneous critical path.

4.  Preserve the programme file, update and progress records used for the analysis.

5.  Maintain a mitigation log and update EOT particulars as the event develops.

## Minimum Ownership

| Role | Responsibility |
| --- | --- |
| Planner | Own programme status and time impact analysis. |
| Contract Administrator | Own notice, entitlement and submission compliance. |
| Site Team | Provide contemporaneous factual records. |
| Commercial | Assess monetary consequences where recoverable. |
| Project Manager | Approve mitigation / acceleration decisions. |

IMPLEMENTATION PRINCIPLE A toolkit only adds value when someone owns it, deadlines are reviewed routinely, and project teams actually use the outputs in meetings and decisions.

ATLAS™ TOOLKIT 5

PROTECT THE MONEY

Payment, Claims & Commercial Entitlement

Link contract administration to cash flow by structuring payment and claims around entitlement, causation, valuation, evidence and recovery.

# Use & Adaptation Note

This toolkit is a practical contract administration aid. It is intentionally contract-form neutral. Before use, adapt clause references, notice periods, service requirements, terminology, statutory requirements and dispute procedures to the signed contract, its amendments and the governing law. It does not replace project-specific legal advice where legal advice is required.

## 1. Payment Application Checklist

☐ Work completed measured and agreed where possible

☐ Variations included and cross-referenced

☐ Materials on site / off site addressed as permitted

☐ Supporting documents attached

☐ Previous certificates / payments reconciled

☐ Retention correctly calculated

☐ Advance payment recovery checked

☐ Contra charges / set-off reviewed

☐ Tax / statutory requirements checked

☐ Submission date and method compliant

☐ Payment due date diarised

## 2. Payment Application & Certification Tracker

| Application No. | Period | Submitted | Applied Amount | Certified Amount | Due Date | Paid Date | Variance | Outstanding | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

## 3. Claims Register

| Claim Ref | Event | Clause | Notice Ref | Time Claimed | Amount Claimed | Submitted | Response Due | Assessed | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

# 4. Claim Assessment Worksheet

| Claim Ref |  |
| --- | --- |
| CAUSE – What happened? |  |
| ENTITLEMENT – Which clause / legal basis? |  |
| LIABILITY – Who bears the risk? |  |
| EFFECT – What happened to the works? |  |
| CAUSATION – How did the event cause the effect? |  |
| TIME – What extension is sought? |  |
| QUANTUM – What amount is sought? |  |
| VALUATION METHOD – Rates / cost / formula |  |
| EVIDENCE – Key records |  |
| NOTICE COMPLIANCE |  |
| MITIGATION |  |
| RELIEF SOUGHT |  |

## 5. Prolongation / Loss & Expense Evidence Checklist

☐ Site staff cost

☐ Site facilities / offices

☐ Utilities

☐ Plant / equipment standing time

☐ Security

☐ Insurance / bonds extension

☐ Temporary works

☐ Supervision

☐ Subcontractor prolongation

☐ Head office overhead basis where contractually recoverable

☐ Financing / interest where recoverable

☐ Productivity / disruption records

☐ Invoices and payroll records

☐ Period attributable to compensable delay

## 6. Final Account Control Sheet

| Component | Original Contract | Approved Change | Pending Change | Claimed | Certified / Agreed | Forecast Final | Difference |
| --- | --- | --- | --- | --- | --- | --- | --- |

## 7. Payment / Certification Follow-Up Template

| Project |  |
| --- | --- |
| Contract |  |
| Date |  |
| Notice / Letter No. |  |
| To |  |
| From |  |

Subject: OUTSTANDING CERTIFICATION / PAYMENT

We refer to [Application / Certificate] No. [X] submitted / issued on [date].

Under Clause [X], the relevant certification / payment milestone falls on [date]. As at the date of this letter, [amount / certification / response] remains outstanding.

Please arrange the required contractual action and confirm the status by [date]. All rights and remedies arising from delay or non-payment are reserved.

DRAFTING CONTROL Replace all bracketed fields. Verify the clause, notice period, addressee and permitted service method before issue.

CLAIM TEST A claim must establish entitlement, causation, quantum and evidence. A time entitlement does not automatically create a money entitlement; check the actual contract.

# Implementation on a Live Project

1.  Create a payment calendar covering submission, certification and payment dates.

2.  Reconcile every payment application against approved and pending variations.

3.  Open a Claim Ref when an event may produce time or monetary entitlement.

4.  Use the Claim Assessment Worksheet before submitting a major claim.

5.  Keep final account control live throughout the project rather than reconstructing it at completion.

## Minimum Ownership

| Role | Responsibility |
| --- | --- |
| QS / Commercial | Own valuation, payment and quantum. |
| Contract Administrator | Own entitlement, notice and contractual compliance. |
| Planner | Provide time consequences supporting prolongation. |
| Finance | Reconcile receipts, overdue amounts and cash flow. |
| Project Manager | Escalate unresolved commercial exposure. |

IMPLEMENTATION PRINCIPLE A toolkit only adds value when someone owns it, deadlines are reviewed routinely, and project teams actually use the outputs in meetings and decisions.

ATLAS™ TOOLKIT 6

PROTECT THE EVIDENCE

Records, Risk & Dispute Prevention

Create contemporaneous, organised evidence so that important project events can be proven, managed and closed long after they occur.

# Use & Adaptation Note

This toolkit is a practical contract administration aid. It is intentionally contract-form neutral. Before use, adapt clause references, notice periods, service requirements, terminology, statutory requirements and dispute procedures to the signed contract, its amendments and the governing law. It does not replace project-specific legal advice where legal advice is required.

## 1. Evidence Matrix

| Issue / Claim | Fact to Prove | Required Evidence | Evidence Available? | Evidence Ref / Location | Gap / Action | Owner |
| --- | --- | --- | --- | --- | --- | --- |

# 2. Daily Site Record

| Date |  |
| --- | --- |
| Weather / Conditions |  |
| Work Areas / Fronts |  |
| Key Activities |  |
| Labour by Trade |  |
| Plant / Equipment |  |
| Deliveries |  |
| Inspections / Tests |  |
| Instructions Received |  |
| Access Restrictions |  |
| Delays / Disruption |  |
| Rework / Defects |  |
| Safety / Stoppages |  |
| Visitors / Meetings |  |
| Photograph References |  |
| Prepared By / Time |  |

## 3. Photograph & Video Evidence Log

| Photo Ref | Date / Time | Location | Subject / Activity | Reason / Issue | Taken By | File Location |
| --- | --- | --- | --- | --- | --- | --- |

## 4. Meeting Action & Decision Log

| Meeting / Date | Issue | Position / Decision | Action | Owner | Due Date | Status | Evidence / Minutes Ref |
| --- | --- | --- | --- | --- | --- | --- | --- |

# 5. Document Control & Evidence Protocol

Use a unique project issue / change / delay / claim reference where possible.

Keep original source files and preserve metadata where relevant.

Use consistent file naming: YYYY-MM-DD – Ref – Document Type – Short Description – Revision.

Never overwrite a superseded contractual document; retain revision history.

Store proof of issue and receipt for formal correspondence.

Cross-reference photographs, diaries, programmes, minutes and letters to the same issue reference.

Restrict editing of approved / final evidence where appropriate.

Maintain backups in the approved project document environment.

## 6. Contract Risk Register

| Risk Ref | Risk / Issue | Clause / Contract Link | Probability | Impact | Mitigation | Owner | Review Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## 7. Dispute Escalation Tracker

| Issue Ref | Current Level | Last Action | Next Escalation Step | Decision / Response Due | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |

# 8. Dispute Escalation Ladder

1.  Site-level clarification and record

2.  Formal contractual correspondence / notice

3.  Project leadership review

4.  Contractual determination / certification process

5.  Senior management negotiation

6.  Mediation / adjudication / dispute board where applicable

7.  Arbitration or litigation where applicable

## 9. Project Close-Out / Lessons Learned Checklist

☐ Open notices reconciled

☐ Variations reconciled

☐ Claims status confirmed

☐ EOT position closed or clearly reserved

☐ Payment / final account status reconciled

☐ Security / retention release dates diarised

☐ Defects and completion records archived

☐ Key evidence folders indexed

☐ Disputes and reservations recorded

☐ Lessons learned captured for future projects

GOLDEN RULE If it is important, record it contemporaneously. Memory deteriorates; a properly controlled record survives.

# Implementation on a Live Project

1.  Agree the project evidence filing convention at mobilisation.

2.  Make Daily Site Records a controlled routine, not an optional diary.

3.  Use the Evidence Matrix for every significant delay, variation and claim.

4.  Turn meeting minutes into tracked actions with owners and deadlines.

5.  Archive project close-out evidence so future claims or audits can be reconstructed quickly.

## Minimum Ownership

| Role | Responsibility |
| --- | --- |
| Document Controller | Own controlled storage, revision and retrieval. |
| Site Team | Create contemporaneous factual records. |
| Contract Administrator | Connect records to clauses, notices and issues. |
| Project / Commercial Leads | Identify evidence gaps and escalation needs. |
| Legal / Claims Advisor | Advise where privilege or dispute protocols apply. |

IMPLEMENTATION PRINCIPLE A toolkit only adds value when someone owns it, deadlines are reviewed routinely, and project teams actually use the outputs in meetings and decisions.